## Sheet1
[5 empty] | Duration (hrs) | Estimate (hrs) | % complete
Learning/Logging |  |  |  |  | 53.5 | 68 | 78.6765
> | Watch lynda.com tutorials (Unity) |  |  |  | 10 | 10 | 100
> | Daily journal entries |  |  |  | 22 | 28 | 78.5714
> | Weekly project planning |  |  |  | 21.5 | 30 | 71.6667
Research |  |  |  |  | 50 | 50 | 100
> | Board game prototype |  |  |  | 11 | 11 | 100
> | Pixel/8 bit character art |  |  |  | 6 | 6 | 100
> | Game music |  |  |  | 5 | 5 | 100
> | Gameplay prototype |  |  |  | 28 | 28 | 100
Development |  |  |  |  | 151.5 | 181.5 | 83.4711
> | Drawing |  |  |  | 58 | 58 | 100
| > | Characters |  |  | 6 | 6 | 100
| > | Walk, idle animations |  |  | 18 | 18 | 100
| > | Attack animation |  |  | 6 | 6 | 100
| > | Zombies |  |  | 5 | 5 | 100
| > | LIT campus layout |  |  | 8.5 | 8.5 | 100
| > | Collectables |  |  | 2 | 2 | 100
| > | Start/end screen |  |  | 5.5 | 5.5 | 100
| > | Animations and cycles |  |  | 2 | 2 | 100
| > | Weapons and health |  |  | 5 | 5 | 100
> | Audio |  |  |  | 21 | 27.5 | 76.3636
| > | Record and edit foley |  |  | 4.5 | 6 | 75
| > | Produce audio and music |  |  | 16.5 | 21.5 | 76.7442
|  | > | start screen |  | 4 | 4 | 100
|  | > | death screen |  | 0.5 | 0.5 | 100
|  | > | hit |  |  | 2 | 0
|  | > | one-liners (lecturers) |  |  | 3 | 0
|  | > | play screen (in game) |  | 12 | 12 | 100
> | Creating the game |  |  |  | 72.5 | 96
| > | Player
|  | > | collision |  | 1 | 1 | 100
|  | > | moving (keys) |  | 4 | 4 | 100
|  | > | animations |  | 24 | 26 | 92.3077
|  | > | collecting, scoring, health |  | 1 | 1 | 100
|  | > | blood particle effect |  | 1 | 1 | 100
| > | Interactive objects
|  | > | props |  | 1 | 1 | 100
|  | > | vending machine |  | 0.5 | 2 | 25
| > | Zombie AI
|  | > | animations |  | 5 | 5 | 100
|  | > | general AI (attacking, walking) |  | 7 | 8 | 87.5
|  | > | spawning |  | 5 | 5 | 100
| > | Level
|  | > | building |  | 13.5 | 13.5 | 100
|  | > | camera |  | 0.5 | 0.5 | 100
|  | > | round increment |  | 2.5 | 2.5 | 100
|  | > | scene handling |  | 0 | 4 | 0
| > | Error/Warning Handling/Bug Fix |  |  | 2 | 4 | 50
| > | Sound |  |  | 0.5 | 5 | 10
| > | Scenes
|  | > | start menu |  | 0.5 | 3 | 16.6667
|  | > | pause menu |  | 3.5 | 3.5 | 100
|  | > | death screen |  |  | 2 | 0
|  | > | how to play screen |  |  | 2 | 0
| > | Publishing |  |  |  | 2 | 0
|  |  |  | TOTAL: | 255 | 299.5 | 85.1419