## Sheet1
[5 empty] | Duration (hrs) | Estimate (hrs) | % complete
Learning/Logging |  |  |  |  | 41.5 | 68 | 61.0294 | Assigned to |  | Weeks Assigned
> | Watch lynda.com tutorials (Unity) |  |  |  | 10 | 10 | 100 | Aaron | Sinead | Week 1-3
> | Daily journal entries |  |  |  | 14 | 28 | 50 | Aaron | Sinead
> | Weekly project planning |  |  |  | 17.5 | 30 | 58.3333 | Aaron | Sinead
Research |  |  |  |  | 50 | 50 | 100
> | Board game prototype |  |  |  | 11 | 11 | 100 | Aaron | Sinead | Week 1-2
> | Pixel/8 bit character art |  |  |  | 6 | 6 | 100 |  | Sinead | Week 2-3
> | Game music |  |  |  | 5 | 5 | 100 | Aaron |  | Week 2-3
> | Gameplay prototype |  |  |  | 28 | 28 | 100 | Aaron | Sinead | Week 2-8
Development |  |  |  |  | 63.5 | 162 | 39.1975
> | Drawing |  |  |  | 37.5 | 51 | 73.5294 |  | Sinead | Week 2-8
| > | Characters |  |  | 6 | 6 | 100 |  | Sinead
| > | Walk animation |  |  | 15.5 | 19 | 81.5789 |  | Sinead
| > | Zombies |  |  | 4 | 12 | 33.3333 |  | Sinead
| > | LIT campus layout |  |  | 4 | 4 | 100 |  | Sinead
| > | Collectables |  |  | 2 | 2 | 100 |  | Sinead
| > | Start/end screen |  |  |  | 2 | 0 |  | Sinead
| > | Animations and cycles |  |  | 1 | 1 | 100 |  | Sinead
| > | Weapons and health |  |  | 5 | 5 | 100 |  | Sinead
> | Audio |  |  |  | 12 | 38 | 31.5789
| > | Record and edit foley |  |  |  | 6 | 0 | Aaron | Sinead | Week 3-10
| > | Produce audio and music |  |  | 12 | 32 | 37.5 | Aaron
|  | > | splash screen |  | 4 | 6 | 66.6667 | Aaron
|  | > | death screen |  |  | 5 | 0 | Aaron
|  | > | hit |  |  | 4 | 0 | Aaron
|  | > | one-liners (lecturers) |  |  | 3 | 0 | Aaron
|  | > | collecting things |  |  | 2 | 0 | Aaron
|  | > | play screen (in game) |  | 8 | 12 | 66.6667 | Aaron
> | Creating the game |  |  |  | 14 | 73 |  |  |  | Week 5-13
| > | Player
|  | > | collision |  |  | 1 | 0 | Aaron
|  | > | moving (keys) |  | 4 | 4 | 100 | Aaron
|  | > | animations |  | 4 | 10 | 40 | Aaron
|  | > | collecting |  |  | 2 | 0 | Aaron
| > | Interactive objects
|  | > | pushing |  |  | 2 | 0 | Aaron
|  | > | doors |  |  | 2 | 0 | Aaron
|  | > | collecting |  |  | 2 | 0 | Aaron
|  | > | switches |  |  | 2 | 0 | Aaron
|  | > | deadly objects |  |  | 2 | 0 | Aaron
| > | Zombie AI
|  | > | animations |  |  | 12 | 0 |  | Sinead
|  | > | general AI (attacking, walking) |  |  | 4 | 0 |  | Sinead
|  | > | spawning |  |  | 5 | 0 |  | Sinead
| > | Level
|  | > | building |  | 6 | 9 | 66.6667 |  | Sinead
|  | > | camera |  |  | 2 | 0 |  | Sinead
|  | > | lighting |  |  | 2 | 0 |  | Sinead
| > | Sound |  |  |  | 5 | 0 | Aaron
| > | Scenes
|  | > | splash screen |  |  | 3 | 0 |  | Sinead
|  | > | level timers |  |  | 2 | 0 |  | Sinead
| > | Publishing |  |  |  | 2 | 0 | Aaron | Sinead | Week 14
|  |  |  | TOTAL: | 155 | 280 | 55.3571 | 25 | 25