## Sheet1
Learning/Logging |  |  |  | Duration (hrs) | Assigned to |  | Weeks Assigned
> | Watch lynda.com tutorials (Unity) |  |  | 10 | Aaron | Sinead | Week 1-3
> | Learn audio program |  |  | n/a | Aaron |  | Week 1-3
> | Lynda videos for C# |  |  | n/a | ? | ? | Week 1-3
> | Daily journal entries |  |  | 5 | Aaron | Sinead
> | Weekly project planning |  |  | 12 | Aaron | Sinead
Research
> | Board game prototype |  |  | 11 | Aaron | Sinead | Week 1-2
> | Pixel/8 bit character art |  |  | 4 |  | Sinead | Week 2-3
> | Game music |  |  | 5 | Aaron |  | Week 2-3
> | Gameplay prototype |  |  |  | Aaron | Sinead | Week 2-4
Development
> | Drawing |  |  |  |  | Sinead | Week 2-7
| > | Characters |  | 4 |  | Sinead
| > | Walk animation |  |  |  | Sinead
| > | Zombies |  |  |  | Sinead
| > | LIT campus layout |  |  |  | Sinead
| > | Collectables |  |  |  | Sinead
| > | Start/end screen |  |  |  | Sinead
| > | Health |  |  |  | Sinead
| > | Animations and cycles |  |  |  | Sinead
> | Audio
| > | Record and edit foley |  |  | Aaron | Sinead | Week 3-9
| > | Produce audio and music |  |  | Aaron
|  | > | splash screen |  | Aaron
|  | > | death screen |  | Aaron
|  | > | jump |  | Aaron
|  | > | walk |  | Aaron
|  | > | hit |  | Aaron
|  | > | one-liners (lecturers) |  | Aaron
|  | > | collecting things |  | Aaron
|  | > | play screen |  | Aaron
> | Creating the game | [5 empty] | Week 5-11
| > | Add characters (hero and zombie sprites) |  |  |  | Sinead
| > | Building animations |  |  |  | Sinead
| > | Player
|  | > | collision |  | Aaron
|  | > | moving |  | Aaron
|  | > | animation |  | Aaron
|  | > | collecting |  | Aaron
| > | Interactive objects
|  | > | pushing |  | Aaron
|  | > | doors |  | Aaron
|  | > | collecting |  | Aaron
|  | > | switches |  | Aaron
|  | > | deadly objects |  | Aaron
| > | Zombie AI
|  | > | walking |  |  | Sinead
|  | > | animation |  |  | Sinead
|  | > | general AI (attacking, platform) |  |  | Sinead
| > | Level
|  | > | building |  |  | Sinead
|  | > | camera |  |  | Sinead
|  | > | lighting |  |  | Sinead
| > | Sound |  |  | Aaron
| > | Scenes
|  | > | splash screen |  |  | Sinead
|  | > | level timers |  |  | Sinead
| > | Publishing |  |  | Aaron | Sinead | Week 12
[5 empty] | 28 | 27