## Sheet1
[5 empty] | Duration (hrs) | Estimate (hrs) | % complete
Learning/Logging |  |  |  |  | 60.5 | 68 | 88.9706
> | Watch lynda.com tutorials (Unity) |  |  |  | 10 | 10 | 100
> | Daily journal entries |  |  |  | 26 | 28 | 92.8571
> | Weekly project planning |  |  |  | 24.5 | 30 | 81.6667
Research |  |  |  |  | 50 | 50 | 100
> | Board game prototype |  |  |  | 11 | 11 | 100
> | Pixel/8 bit character art |  |  |  | 6 | 6 | 100
> | Game music |  |  |  | 5 | 5 | 100
> | Gameplay prototype |  |  |  | 28 | 28 | 100
Development |  |  |  |  | 194 | 215.5 | 90.0232
> | Drawing |  |  |  | 58.5 | 61 | 95.9016
| > | Characters |  |  | 6 | 6 | 100
| > | Walk, idle animations |  |  | 18 | 18 | 100
| > | Attack animation |  |  | 6 | 6 | 100
| > | Zombies |  |  | 5 | 5 | 100
| > | LIT campus layout |  |  | 9 | 9 | 100
| > | Collectables |  |  | 2 | 2 | 100
| > | Start/end/other screen |  |  | 5.5 | 8 | 68.75
| > | Animations and cycles |  |  | 2 | 2 | 100
| > | Weapons and health |  |  | 5 | 5 | 100
| > | UI |  |  | 6.25 | 6 | 104.1667
> | Audio |  |  |  | 24.5 | 25.5 | 96.0784
| > | Record and edit foley |  |  | 6 | 6 | 100
| > | Produce audio and music |  |  | 18.5 | 19.5 | 94.8718
|  | > | start screen |  | 4 | 4 | 100
|  | > | death screen |  | 0.5 | 0.5 | 100
|  | > | one-liners (lecturers) |  | 2 | 3 | 66.6667
|  | > | play screen (in game) |  | 12 | 12 | 100
> | Creating the game |  |  |  | 111 | 129 | 116.2162
| > | Player
|  | > | collision |  | 1 | 1 | 100
|  | > | moving (keys) |  | 4 | 4 | 100
|  | > | animations |  | 32.5 | 32.5 | 100
|  | > | collecting, scoring, health, Bernie |  | 11 | 11 | 100
|  | > | blood particle effect |  | 1 | 1 | 100
| > | Interactive objects
|  | > | props |  | 1 | 1 | 100
|  | > | vending machine |  | 4 | 4 | 100
| > | Zombie AI
|  | > | animations |  | 5 | 5 | 100
|  | > | general AI (attacking, walking) |  | 7 | 7 | 100
|  | > | spawning |  | 5 | 5 | 100
|  | > | 2D Nav AI asset |  | 10.5 | 12 | 87.5
| > | Level
|  | > | building |  | 13.5 | 13.5 | 100
|  | > | camera |  | 0.5 | 0.5 | 100
|  | > | round increment |  | 2.5 | 2.5 | 100
|  | > | scene handling |  | 1.5 | 4 | 37.5
| > | Error/Warning Handling/Bug Fix |  |  | 2 | 4 | 50
| > | Sound |  |  | 1.5 | 5 | 30
| > | Scenes
|  | > | start menu |  | 0.5 | 3 | 16.6667
|  | > | pause menu |  | 3.5 | 3.5 | 100
|  | > | death screen |  |  | 2 | 0
|  | > | how to play screen |  |  | 2 | 0
|  | > | stats screen |  | 3.5 | 3.5 | 100
| > | Publishing |  |  |  | 2 | 0
|  |  |  | TOTAL: | 304.5 | 333.5 | 91.3043