## Sheet1
[5 empty] | Duration (hrs) | Estimate (hrs) | % complete
Learning/Logging |  |  |  |  | 50.5 | 68 | 74.2647
> | Watch lynda.com tutorials (Unity) |  |  |  | 10 | 10 | 100
> | Daily journal entries |  |  |  | 20 | 28 | 71.4286
> | Weekly project planning |  |  |  | 20.5 | 30 | 68.3333
Research |  |  |  |  | 50 | 50 | 100
> | Board game prototype |  |  |  | 11 | 11 | 100
> | Pixel/8 bit character art |  |  |  | 6 | 6 | 100
> | Game music |  |  |  | 5 | 5 | 100
> | Gameplay prototype |  |  |  | 28 | 28 | 100
Development |  |  |  |  | 130.5 | 190.5 | 68.5039
> | Drawing |  |  |  | 55 | 66.5 | 82.7068
| > | Characters |  |  | 6 | 6 | 100
| > | Walk, idle animations |  |  | 18 | 19 | 94.7368
| > | Attack animation |  |  | 3 | 12 | 25
| > | Zombies |  |  | 5 | 5 | 100
| > | LIT campus layout |  |  | 8.5 | 10 | 85
| > | Collectables |  |  | 2 | 2 | 100
| > | Start/end screen |  |  | 5.5 | 5.5 | 100
| > | Animations and cycles |  |  | 2 | 2 | 100
| > | Weapons and health |  |  | 5 | 5 | 100
> | Audio |  |  |  | 16 | 38 | 42.1053
| > | Record and edit foley |  |  |  | 6 | 0
| > | Produce audio and music |  |  | 16 | 32 | 50
|  | > | splash screen |  | 4 | 6 | 66.6667
|  | > | death screen |  |  | 5 | 0
|  | > | hit |  |  | 4 | 0
|  | > | one-liners (lecturers) |  |  | 3 | 0
|  | > | collecting things |  |  | 2 | 0
|  | > | play screen (in game) |  | 12 | 12 | 100
> | Creating the game |  |  |  | 59.5 | 86
| > | Player
|  | > | collision |  | 1 | 1 | 100
|  | > | moving (keys) |  | 4 | 4 | 100
|  | > | animations |  | 21 | 22 | 95.4545
|  | > | collecting, scoring, health |  | 1 | 1 | 100
|  | > | blood particle effect |  | 1 | 1 | 100
| > | Interactive objects
|  | > | pushing props |  |  | 1 | 0
|  | > | vending machine |  |  | 2 | 0
| > | Zombie AI
|  | > | animations |  | 5 | 5 | 100
|  | > | general AI (attacking, walking) |  | 6 | 8 | 75
|  | > | spawning |  | 5 | 5 | 100
| > | Level
|  | > | building |  | 11.5 | 13 | 88.4615
|  | > | camera |  | 1 | 1 | 100
|  | > | round increment |  | 2.5 | 4 | 62.5
|  | > | scene handling |  |  | 4 | 0
| > | Error/Warning Handling |  |  | 0.5 | 2 | 25
| > | Sound |  |  |  | 5 | 0
| > | Scenes
|  | > | splash screen |  |  | 3 | 0
|  | > | level timers |  |  | 2 | 0
| > | Publishing |  |  |  | 2 | 0
|  |  |  | TOTAL: | 231 | 308.5 | 74.8784